## Start Here
Wedding Budget Planner & Tracker
Budget, payments, vendors, guest list and a 12-month checklist in one workbook. Works in Excel and Google Sheets.
QUICK START (10 minutes)
1. 'Dashboard': type your wedding date and total budget in the two yellow cells at the top. Everything else counts from them.
2. 'Budget': each category gets a share of your total (typical % shown for guidance). Change 'Your %' to suit you,
or type a fixed dollar amount (e.g. a quote you already have) and it replaces the % for that category.
3. 'Vendors': one row per vendor: contact details, status, contract total and deposit. Paid so far, balance and next due date fill in.
4. 'Payments': log every deposit, payment and invoice. Status 'Paid' = money gone; 'Owed' = still to pay (add the due date).
Owed payments past their due date turn orange. Refund or credit? Enter a negative amount.
5. 'Guest List': one row per invited guest; RSVP, meal, plus-one and table. Headcounts and a catering estimate update live.
Your side names, meal options and catering cost per guest are the yellow cells on the right of that tab.
6. 'Checklist': 50 planning tasks with due dates counted back from your wedding date. Mark 'Yes' when done; add your own tasks.
7. Red cells mean a row needs fixing (text in an amount, a date that isn't a date, a category or vendor not on your list).
That row stays out of the totals until fixed. The count shows at the top of each tab and on the Dashboard.
8. Delete the EXAMPLE rows first. Room for 500 payments, 40 vendors, 500 guests and 120 tasks.
Need more? Right-click a row number in the middle of a list > Insert; totals expand automatically.
HOW THE NUMBERS WORK
Committed = everything paid + everything still owed. Remaining = total budget - committed. % used = committed / total budget.
Budget per category = total budget x your %, unless you typed a fixed amount. 'Unallocated' on the Budget tab shows what is left to assign.
Guests attending = 'Yes' RSVPs plus their plus-ones. Catering estimate = (attending + not yet replied) x cost per guest.
Checklist due date = wedding date minus the months in 'Months before' (0.5 = 2 weeks, 0.25 = 1 week, -1 = a month after).
COLOR KEY
Yellow cells = you type here. White cells = formulas, leave them alone. Red = fix this. Orange = overdue or over budget.
USING GOOGLE SHEETS?
Open sheets.google.com > File > Import > Upload this .xlsx > 'Replace spreadsheet'. Formulas and dropdowns carry over.
Questions or a formula not behaving? Email nora@qnsai.com. Made by Nora Studio. Congratulations!

## Dashboard
Wedding Dashboard
Wedding date: | Total budget: | 30000 | Type your wedding date in C3. Updates automatically from every tab |  | Chart data (do not edit)
[5 empty] | Category | Budget | Committed
TOTAL BUDGET |  |  | COMMITTED (PAID + OWED) | REMAINING | Venue | 6000 | 12000
30000 |  |  | 12000 | 18000 | Catering & bar | 7500 | 0
[5 empty] | Photography | 3000 | 0
[5 empty] | Videography | 1200 | 0
% OF BUDGET USED |  |  | PAID SO FAR | STILL OWED | Attire | 1800 | 0
40% |  |  | 3000 | 9000 | Hair & makeup | 600 | 0
[5 empty] | Flowers & decor | 2400 | 0
[5 empty] | Music & entertainment | 1500 | 0
DAYS TO THE WEDDING |  |  | OVERDUE PAYMENTS | NEXT PAYMENT DUE | Wedding planner | 900 | 0
Set your date |  |  | 0 | 2027-05-01 | Rings | 900 | 0
[5 empty] | Cake & desserts | 600 | 0
[5 empty] | Stationery | 600 | 0
GUESTS ATTENDING |  |  | CATERING ESTIMATE | CHECKLIST DONE | Rentals | 600 | 0
2 |  |  | 285 | 0% | Transportation | 600 | 0
[5 empty] | Favors & gifts | 300 | 0
[5 empty] | Officiant & license | 300 | 0
RSVPs still out: 1 ¦ Overdue payments: 0 ¦ Overdue tasks: 0 ¦ Tasks done: 0 of 50 |  |  |  |  | Contingency / other | 1200 | 0
Committed = paid + still owed. Catering estimate = (attending + not replied) x cost per guest (Guest List tab). | [5 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[5 empty] | Month | Paid | Owed (by due date)
[5 empty] | Earlier | 0 | 0
[5 empty] | Jun 25 | 0 | 0
[5 empty] | Jul 25 | 0 | 0
[5 empty] | Aug 25 | 0 | 0
[5 empty] | Sep 25 | 0 | 0
[5 empty] | Oct 25 | 0 | 0
[5 empty] | Nov 25 | 0 | 0
[5 empty] | Dec 25 | 0 | 0
[5 empty] | Jan 26 | 0 | 0
[5 empty] | Feb 26 | 0 | 0
[5 empty] | Mar 26 | 0 | 0
[5 empty] | Apr 26 | 0 | 0
[5 empty] | May 26 | 0 | 0
[5 empty] | Jun 26 | 0 | 0
[5 empty] | Jul 26 | 0 | 0
[5 empty] | Aug 26 | 0 | 0
[5 empty] | Sep 26 | 3000 | 0
[5 empty] | Oct 26 | 0 | 0
[5 empty] | Nov 26 | 0 | 0
[5 empty] | Later | 0 | 9000
[5 empty] | No due date | 0 | 0
[5 empty] | Status | Amount
[5 empty] | Paid | 3000
[5 empty] | Still owed | 9000
[5 empty] | Not yet committed | 18000
[5 empty] | Vendor | Paid | Owed
[5 empty] | EXAMPLE Venue | 3000 | 9000
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0

## Budget
Budget
Your total budget split by category. Edit 'Your %' or type a fixed amount; spending comes from the Payments tab. | [7 empty] | Rows to fix: | 0
Red cell = something to fix. Orange = category over budget.
Total budget | 30000 | Allocated | 30000 | Unallocated | 0 | (change the total on the Dashboard)
Category | Typical % | Your % | Fixed amount (optional) | Budget | Committed (paid + owed) | Paid | Still owed | Remaining | % used
Venue | 20% | 20% |  | 6000 | 12000 | 3000 | 9000 | -6000 | 200%
Catering & bar | 25% | 25% |  | 7500 | 0 | 0 | 0 | 7500 | 0%
Photography | 10% | 10% |  | 3000 | 0 | 0 | 0 | 3000 | 0%
Videography | 4% | 4% |  | 1200 | 0 | 0 | 0 | 1200 | 0%
Attire | 6% | 6% |  | 1800 | 0 | 0 | 0 | 1800 | 0%
Hair & makeup | 2% | 2% |  | 600 | 0 | 0 | 0 | 600 | 0%
Flowers & decor | 8% | 8% |  | 2400 | 0 | 0 | 0 | 2400 | 0%
Music & entertainment | 5% | 5% |  | 1500 | 0 | 0 | 0 | 1500 | 0%
Wedding planner | 3% | 3% |  | 900 | 0 | 0 | 0 | 900 | 0%
Rings | 3% | 3% |  | 900 | 0 | 0 | 0 | 900 | 0%
Cake & desserts | 2% | 2% |  | 600 | 0 | 0 | 0 | 600 | 0%
Stationery | 2% | 2% |  | 600 | 0 | 0 | 0 | 600 | 0%
Rentals | 2% | 2% |  | 600 | 0 | 0 | 0 | 600 | 0%
Transportation | 2% | 2% |  | 600 | 0 | 0 | 0 | 600 | 0%
Favors & gifts | 1% | 1% |  | 300 | 0 | 0 | 0 | 300 | 0%
Officiant & license | 1% | 1% |  | 300 | 0 | 0 | 0 | 300 | 0%
Contingency / other | 4% | 4% |  | 1200 | 0 | 0 | 0 | 1200 | 0%
Total |  | 100% |  | 30000 | 12000 | 3000 | 9000 | 18000 | 40%
Catering estimate from your Guest List: 3 guests x $95 = $285 ¦ your Catering & bar budget: $7,500
Typical % = rough US averages for guidance only. Your % column should add up to 100% (see Total); spare rows are for your own categories.
Renaming a category? Rename it here first; payments under the old name turn red until you pick the new name.

## Payments
Payments
Every deposit, payment and invoice. Paid = money gone. Owed = still to pay (add the due date). | [5 empty] | Rows to fix: | 0
Red cell = something to fix (row stays out of the totals). Orange row = owed and past its due date.
Date | Category | Vendor (optional) | Description | Amount | Paid / Owed | Due date (if owed) | Alert
2026-09-01 | Venue | EXAMPLE Venue | EXAMPLE: venue deposit | 3000 | Paid
2026-09-01 | Venue | EXAMPLE Venue | EXAMPLE: venue balance | 9000 | Owed | 2027-05-01
Formulas:
Alert = IF(AND([Paid / Owed]="Owed",ISNUMBER([Due date (if owed)])),IF([Due date (if owed)]<TODAY(),"OVERDUE",IF([Due date (if owed)]-TODAY()<=30,"Due in "&([Due date (if owed)]-TODAY())&" days","")),"")

## Vendors
Vendors
Who you're working with. Paid so far, balance and next due date come from the Payments tab. | [8 empty] | Rows to fix: | 0
Red cell = something to fix. Orange = a payment to this vendor is overdue.
Vendor | Category | Contact person | Phone | Email | Status | Contract total | Deposit | Paid so far | Balance due | Next payment due | Notes
EXAMPLE Venue | Venue | Jane Smith | 555-0100 | events@example.com | Booked | 12000 | 3000 | 3000 | 9000 | 2027-05-01
Formulas:
Next payment due = IF(OR([Vendor]="",Calc!F60=0),"",Calc!F60)

## Guest List
Guest List
One row per invited guest. Plus-ones count automatically. Your options are in the yellow cells on the right. | [5 empty] | Rows to fix: |  | 0
Red cell = something to fix. That guest stays out of the headcounts until fixed.
Guest name | Side | Group | RSVP | Meal choice | Plus-one? | Plus-one meal | Table | Address / notes | Your options
EXAMPLE: Aunt Mary | Bride | Family | Yes | Chicken | Yes | Fish | 1 |  | Side 1 | Bride
EXAMPLE: Tom Lee | Groom | College | Pending |  | No |  |  |  | Side 2 | Groom
[9 empty] | Side 3 | Both
[9 empty] | Meal option 1 | Chicken
[9 empty] | Meal option 2 | Beef
[9 empty] | Meal option 3 | Fish
[9 empty] | Meal option 4 | Vegetarian
[9 empty] | Meal option 5 | Kids meal
Meal option 6
[9 empty] | Catering cost per guest | 95
[9 empty] | Headcount | People
[9 empty] | Invited (guests + plus-ones) | 3
[9 empty] | Attending (RSVP Yes) | 2
[9 empty] | Not replied yet | 1
[9 empty] | Declined | 0
[9 empty] | Expected headcount (attending + not replied) | 3
[9 empty] | Catering estimate | 285
[9 empty] | Attending by side | People
[9 empty] | Bride | 2
[9 empty] | Groom | 0
[9 empty] | Both | 0
[9 empty] | No side chosen | 0
[9 empty] | Meals (attending guests) | Meals
[9 empty] | Chicken | 1
[9 empty] | Beef | 0
[9 empty] | Fish | 1
[9 empty] | Vegetarian | 0
[9 empty] | Kids meal | 0
0
[9 empty] | No meal chosen yet | 0
Two brides or two grooms? Just rename the sides above.
Renaming a meal or side turns rows using the old name red.

## Checklist
Checklist
Type your wedding date on the Dashboard and the due dates fill in. |  |  | Rows to fix: |  | 0
Red cell = something to fix. Orange = overdue. Want a different date for a task? Type it in 'Your own due date'.
Task | Months before | Your own due date (optional) | Due date | Done? | Status | Notes
Agree on your total budget and fill in the Budget tab | 12 |  |  |  | No date
Pick a date (or season) and a rough guest count | 12 |  |  |  | No date
Start the guest list | 12 |  |  |  | No date
Research and book the venue | 12 |  |  |  | No date
Decide whether to hire a wedding planner | 12 |  |  |  | No date
Choose your wedding party | 12 |  |  |  | No date
Book the photographer | 10 |  |  |  | No date
Book the videographer | 10 |  |  |  | No date
Book the caterer (if not included with the venue) | 10 |  |  |  | No date
Book the band or DJ | 10 |  |  |  | No date
Set up a wedding website | 10 |  |  |  | No date
Shop for wedding attire | 9 |  |  |  | No date
Book the officiant | 9 |  |  |  | No date
Book the florist | 9 |  |  |  | No date
Register for gifts | 9 |  |  |  | No date
Send save-the-dates | 8 |  |  |  | No date
Reserve hotel room blocks for guests | 8 |  |  |  | No date
Start planning the honeymoon | 8 |  |  |  | No date
Book hair and makeup | 6 |  |  |  | No date
Order the cake | 6 |  |  |  | No date
Book rentals (tables, chairs, linens) | 6 |  |  |  | No date
Book transportation | 6 |  |  |  | No date
Order invitations | 6 |  |  |  | No date
Choose wedding party attire | 5 |  |  |  | No date
Buy wedding rings | 4 |  |  |  | No date
Plan the rehearsal dinner | 4 |  |  |  | No date
Menu tasting and final menu | 4 |  |  |  | No date
Book first attire fitting | 4 |  |  |  | No date
Order favors and welcome bags | 3 |  |  |  | No date
Plan the ceremony with the officiant | 3 |  |  |  | No date
Buy gifts for the wedding party | 3 |  |  |  | No date
Mail invitations | 2 |  |  |  | No date
Check marriage license requirements | 2 |  |  |  | No date
Send must-play / do-not-play lists to the DJ or band | 2 |  |  |  | No date
Chase late RSVPs | 1 |  |  |  | No date
Give the final headcount to the caterer | 1 |  |  |  | No date
Make the seating chart (Table column on Guest List) | 1 |  |  |  | No date
Confirm every vendor, arrival time and payment due date | 1 |  |  |  | No date
Get the marriage license | 1 |  |  |  | No date
Final attire fitting | 1 |  |  |  | No date
Pay or schedule final vendor balances (Payments tab) | 0.5 |  |  |  | No date
Share the day-of timeline with vendors and wedding party | 0.5 |  |  |  | No date
Pack for the honeymoon | 0.5 |  |  |  | No date
Prepare tip envelopes for vendors | 0.25 |  |  |  | No date
Delegate day-of jobs (gifts, decor pick-up) | 0.25 |  |  |  | No date
Wedding day: enjoy it! | 0 |  |  |  | No date
Return rentals and attire | -0.5 |  |  |  | No date
Send thank-you cards | -1 |  |  |  | No date
Change your name on documents (if you are) | -1 |  |  |  | No date
Close out the budget: settle any last balances | -1 |  |  |  | No date
Formulas:
Status = IF([Task]="","",IF([Done?]="Yes","Done",IF([Due date]="","No date",IF([Due date]<TODAY(),"OVERDUE",IF([Due date]-TODAY()<=30,"Due soon","Upcoming")))))

## Lists (hidden)
Valid categories | Category dropdown | Valid vendors | Vendor dropdown | Payment status | Vendor status | Yes/No | RSVP | Done
Venue | Venue | EXAMPLE Venue | EXAMPLE Venue | Paid | Considering | Yes | Yes | Yes
Catering & bar | Catering & bar | [empty vendor 2] |  | Owed | Booked | No | No
Photography | Photography | [empty vendor 3] |  |  | Paid in full |  | Pending
Videography | Videography | [empty vendor 4] |  |  | Cancelled
Attire | Attire | [empty vendor 5]
Hair & makeup | Hair & makeup | [empty vendor 6]
Flowers & decor | Flowers & decor | [empty vendor 7]
Music & entertainment | Music & entertainment | [empty vendor 8]
Wedding planner | Wedding planner | [empty vendor 9]
Rings | Rings | [empty vendor 10]
Cake & desserts | Cake & desserts | [empty vendor 11]
Stationery | Stationery | [empty vendor 12]
Rentals | Rentals | [empty vendor 13]
Transportation | Transportation | [empty vendor 14]
Favors & gifts | Favors & gifts | [empty vendor 15]
Officiant & license | Officiant & license | [empty vendor 16]
Contingency / other | Contingency / other | [empty vendor 17]
[empty slot 18] |  | [empty vendor 18]
[empty slot 19] |  | [empty vendor 19]
[empty slot 20] |  | [empty vendor 20]
[empty vendor 21]
[empty vendor 22]
[empty vendor 23]
[empty vendor 24]
[empty vendor 25]
[empty vendor 26]
[empty vendor 27]
[empty vendor 28]
[empty vendor 29]
[empty vendor 30]
[empty vendor 31]
[empty vendor 32]
[empty vendor 33]
[empty vendor 34]
[empty vendor 35]
[empty vendor 36]
[empty vendor 37]
[empty vendor 38]
[empty vendor 39]
[empty vendor 40]

## Calc (hidden)
Category | Budget | Committed | Paid | Owed
Venue | 6000 | 12000 | 3000 | 9000
Catering & bar | 7500 | 0 | 0 | 0
Photography | 3000 | 0 | 0 | 0
Videography | 1200 | 0 | 0 | 0
Attire | 1800 | 0 | 0 | 0
Hair & makeup | 600 | 0 | 0 | 0
Flowers & decor | 2400 | 0 | 0 | 0
Music & entertainment | 1500 | 0 | 0 | 0
Wedding planner | 900 | 0 | 0 | 0
Rings | 900 | 0 | 0 | 0
Cake & desserts | 600 | 0 | 0 | 0
Stationery | 600 | 0 | 0 | 0
Rentals | 600 | 0 | 0 | 0
Transportation | 600 | 0 | 0 | 0
Favors & gifts | 300 | 0 | 0 | 0
Officiant & license | 300 | 0 | 0 | 0
Contingency / other | 1200 | 0 | 0 | 0
| 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0
Total | 30000 | 12000 | 3000 | 9000
Committed (all valid rows) | 12000
Paid | 3000
Owed | 9000
Overdue $ | 0
Overdue count | 0
Next payment due (today or later) | 46508
Month start | Label | Paid | Owed (by due date)
| Earlier | 0 | 0
45809 | Jun 25 | 0 | 0
45839 | Jul 25 | 0 | 0
45870 | Aug 25 | 0 | 0
45901 | Sep 25 | 0 | 0
45931 | Oct 25 | 0 | 0
45962 | Nov 25 | 0 | 0
45992 | Dec 25 | 0 | 0
46023 | Jan 26 | 0 | 0
46054 | Feb 26 | 0 | 0
46082 | Mar 26 | 0 | 0
46113 | Apr 26 | 0 | 0
46143 | May 26 | 0 | 0
46174 | Jun 26 | 0 | 0
46204 | Jul 26 | 0 | 0
46235 | Aug 26 | 0 | 0
46266 | Sep 26 | 3000 | 0
46296 | Oct 26 | 0 | 0
46327 | Nov 26 | 0 | 0
46357 | Later | 0 | 9000
| No due date | 0 | 0
| Check total | 12000
Vendor | Committed | Paid | Owed | Next due | Sort key
EXAMPLE Venue | 12000 | 3000 | 9000 | 46508 | 12000
| 0 | 0 | 0 | 0 | -1.001
| 0 | 0 | 0 | 0 | -1.002
| 0 | 0 | 0 | 0 | -1.003
| 0 | 0 | 0 | 0 | -1.004
| 0 | 0 | 0 | 0 | -1.005
| 0 | 0 | 0 | 0 | -1.006
| 0 | 0 | 0 | 0 | -1.007
| 0 | 0 | 0 | 0 | -1.008
| 0 | 0 | 0 | 0 | -1.009
| 0 | 0 | 0 | 0 | -1.01
| 0 | 0 | 0 | 0 | -1.011
| 0 | 0 | 0 | 0 | -1.012
| 0 | 0 | 0 | 0 | -1.013
| 0 | 0 | 0 | 0 | -1.014
| 0 | 0 | 0 | 0 | -1.015
| 0 | 0 | 0 | 0 | -1.016
| 0 | 0 | 0 | 0 | -1.017
| 0 | 0 | 0 | 0 | -1.018
| 0 | 0 | 0 | 0 | -1.019
| 0 | 0 | 0 | 0 | -1.02
| 0 | 0 | 0 | 0 | -1.021
| 0 | 0 | 0 | 0 | -1.022
| 0 | 0 | 0 | 0 | -1.023
| 0 | 0 | 0 | 0 | -1.024
| 0 | 0 | 0 | 0 | -1.025
| 0 | 0 | 0 | 0 | -1.026
| 0 | 0 | 0 | 0 | -1.027
| 0 | 0 | 0 | 0 | -1.028
| 0 | 0 | 0 | 0 | -1.029
| 0 | 0 | 0 | 0 | -1.03
| 0 | 0 | 0 | 0 | -1.031
| 0 | 0 | 0 | 0 | -1.032
| 0 | 0 | 0 | 0 | -1.033
| 0 | 0 | 0 | 0 | -1.034
| 0 | 0 | 0 | 0 | -1.035
| 0 | 0 | 0 | 0 | -1.036
| 0 | 0 | 0 | 0 | -1.037
| 0 | 0 | 0 | 0 | -1.038
| 0 | 0 | 0 | 0 | -1.039
Top vendors | Key | Row | Paid | Owed
EXAMPLE Venue | 12000 | 1 | 3000 | 9000
| -1.001 | 2 | 0 | 0
| -1.002 | 3 | 0 | 0
| -1.003 | 4 | 0 | 0
| -1.004 | 5 | 0 | 0
| -1.005 | 6 | 0 | 0
| -1.006 | 7 | 0 | 0
| -1.007 | 8 | 0 | 0
Tasks | 50
Done | 0
Overdue tasks | 0
Done % | 0